EXHIBIT III

CONTRACT ADMINISTRATION

TABLE OF CONTENTS

1.	General	2

2.	CLIENT Requirements	2

3.	CONTRACTOR’s Organization and PERSONNEL	2

3.1	Organization	2

3.2	Contractor Personnel	2

4.	Correspondence and Communication	3

4.1	Correspondence	3

4.2	Confidential Correspondence	4

4.3	Receipt of Correspondence	4

4.4	Correspondence Register	4

4.5	Data Transmission	4

4.6	Oral Communication	4

4.7	Notices Under the CONTRACT	4

4.8	Urgent Communication	5

5.	Planning, Progress and Reporting – Not Applicable	5

6.	Call-Off and CHANGES to the SERVICES	5

6.1	Call-Off of SERVICES	5

6.2	Completion of the SERVICES	5

6.3	CHANGES	6

6.4	CHANGE of the SERVICES	6

6.5	CHANGE Register	7

6.6	Issue and approval of CHANGE	7

7.	Cost Management, Invoicing and Payment	8

7.1	General Procedures	8

7.2	Timesheets	8

7.3	Invoicing	8

7.4	Supporting Documentation	8

7.5	Close Out of Call-Off Work Orders	9

7.6	Financial Close Out	9

8.	Representatives of the PARTIES	9

9.	CONTRACT Close Out	9

10.	Attachments	10

# General

CLIENT requires that CONTRACTOR uses its own systems, methods and procedures in the performance of the SERVICES.  However, CLIENT has specific requirements regarding quality, consistency, and project control with which CONTRACTOR shall comply, and these are addressed in this EXHIBIT III.

# CLIENT Requirements

Any specific requirements of CLIENT will be issued by the CLIENT REPRESENTATIVE and will be given in writing; verbal request for any actions that have a contractual impact shall not be accepted by CONTRACTOR.

Such specific requirements may include instructions to proceed with or suspend SERVICES or specific changes to the SERVICES or part thereof or the methods for executing the SERVICES which CLIENT considers to be the basis for a CHANGE and which shall be priced in accordance with EXHIBIT II – COMPENSATION and administered in accordance with Section 6 below.

If CONTRACTOR believes any specific requirements, instruction or specific work description contained in any other notice or communication issued by CLIENT does not form a part of the SERVICES, then CONTRACTOR shall submit a CHANGE Proposal as set out in Section 6 of this EXHIBIT III for due consideration and response by CLIENT.

# CONTRACTOR’s Organization and PERSONNEL

  - Organization

CONTRACTOR’s organization charts for the performance of the SERVICES, stating job titles and showing reporting relationships to CONTRACTOR’s REPRESENTATIVE are shown in Attachment 1 hereto.

CONTRACTOR shall maintain its organization charts and submit same for approval in the event of any change.

  - Contractor Personnel

- The list of KEY PERSONNEL, who will be engaged in the SERVICES, is attached as Attachment 2 hereto. The personnel, who are provided by CONTRACTOR to Vietnam or any other places required for the execution of this CONTRACT, shall have been found fit for their assignments, and their qualifications must be acceptable to CLIENT.

- Except for the KEY PERSONNEL named in Attachment 2 hereto, CONTRACTOR shall send for each other position at least three (03) Curriculum Vitae to CLIENT for approval as soon as possible but not later than fourteen (14) days prior to departure of such personnel. Such Curriculum Vitae shall be substantially in the form as stated in Attachment 2 hereto.

- The following criteria shall be applied by CONTRACTOR in selecting and by CLIENT in consideration of acceptance of KEY PERSONNEL:

- KEY PERSONNEL shall have been physically examined and found fit for their assignment:

- KEY PERSONNEL shall read, write, understand and speak English fluently;

- KEY PERSONNEL shall meet or exceed the qualifications and experiences as stipulated in scope of SERVICES; and

- KEY PERSONNEL shall be competent in the performance of the SERVICES to which they are deployed.

CONTRACTOR shall ensure that its KEY PERSONNEL continues to perform the part of SERVICES assigned to them as long as necessary to achieve the execution program of the PROJECT.

- Notwithstanding the prior acceptance, CLIENT shall have the right to require CONTRACTOR to replace any KEY personnel, if such personnel misconduct or proves to be incompetent or negligent or any other reason deemed appropriate by CLIENT. If CLIENT requests to replace any person of CONTRACTOR, CONTRACTOR shall within seven (7) DAYS arrange for a replacement by a person of comparable competence, subject to CLIENT approval. The cost of replacements shall be borne by CONTRACTOR.

CLIENT shall, in case of replacement, have the right to deduct from any amount due to or owing to CONTRACTOR an amount equivalent to the daily rate of such removed personnel multiplied by the number of days counting from and including the day of CLIENT’S request until such personnel is replaced.

- CONTRACTOR shall use the designated PERSONNEL specifically identified in Attachment 2 hereto as required for the entire the term of the CONTRACT. CONTRACTOR shall not re-assign any of these KEY PERSONNEL to work on or provide any services related to any of CONTRACTOR’s (or its Affiliate or subsidiaries) other projects without CLIENT’s prior written approval, which would not be unreasonably withheld.

- CLIENT shall have the right to adjust the mobilization and demobilization schedule of PERSONNEL.

- CONTRACTOR is encouraged, to the extent practicable and reasonable, to employ local staff and other resources from sources within Vietnam.

# Correspondence and Communication

  - Correspondence

All correspondence and communications between the PARTIES in connection with the CONTRACT shall be made in writing and shall be addressed and directed by CONTRACTOR’s REPRESENTATIVE to the CLIENT REPRESENTATIVE or vice versa. Each item of correspondence issued by CLIENT and CONTRACTOR shall have a unique and sequential reference.

  - Confidential Correspondence

All correspondence and communications which contain information which is required to be maintained as confidential shall be marked clearly ‘Confidential’.

  - Receipt of Correspondence

All correspondence shall be date stamped upon receipt by the receiving PARTY.

  - Correspondence Register

CONTRACTOR shall maintain a chronological register of all incoming and outgoing correspondence and communications in connection with the CONTRACT.  This register shall be available for review by CLIENT upon request.

  - Data Transmission

All data including reports, drawings, and other technical documents shall be accompanied by a transmittal note in the sending PARTY’S normal form.  The recipient of such documents shall sign the transmittal note and return the copy of the transmittal note to the initiator.  The initiator shall be responsible for ensuring that all such transmittals have been acknowledged as received by the recipient.

Any technical documents issued by either PARTY which require the review and response from the other PARTY shall be reviewed and returned by the other PARTY within fifteen (15) working days.

As part of the final documentation package, all Deliverables shall be provided by CONTRACTOR as follows:

| 1. | Original document | One (1) |
| --- | --- | --- |
| 2. | Hard copy of original document | Two (2) |
| 3. | USB with all documents | Two (2) |

  - Oral Communication

Oral communication of CLIENT’s instructions and/or oral communications regarding other technical or contractual matters between the PARTIES shall not be acted on before being confirmed in writing.

  - Notices Under the CONTRACT

All directions, instructions, notifications, agreements, authorizations, approvals, acknowledgements and general correspondence shall be considered as notices under the CONTRACT and shall be delivered in accordance with Clause 25.5 of GENERAL TERMS AND CONDITIONS.

All correspondence and communications shall be dated and uniquely numbered and documents of a single type (e.g. transmittal notes, CLIENT’s letters, CLIENT’s Directions, CHANGE Requests) shall be numbered consecutively by the issuing PARTY. Each item of correspondence or communication shall carry the CONTRACT number and its unique document number for identification purposes.  CONTRACTOR shall maintain a register of all correspondence and communications and provide the CLIENT REPRESENTATIVE with copies at least on a weekly basis or as and when requested by the CLIENT REPRESENTATIVE.

Whenever technical documentation is referred to in or is attached to any correspondence or communication, such correspondence or communication shall include the respective document number(s), revision indicator(s) and revision status within the primary document text.

All correspondence and communications shall identify to whom copies have been sent.

  - Urgent Communication

Any correspondence or communication which is of an urgent nature shall include the word ‘Urgent’ immediately in front of the name(s) of the primary recipient(s).

# Planning, Progress and Reporting – Not Applicable

# Call-Off and CHANGES to the SERVICES

  - Call-Off of SERVICES

- The Service Order, as per Attachment 4 and Attachment 5, shall be used to initiate all SERVICES as required by CLIENT, as specifically addressed hereunder.

- CLIENT will issue a regular summary of requirements for the deployment of PERSONNEL including initial information describing scope of SERVICES, work location, tentative work schedule, etc.

- Upon receipt of the summary details, CONTRACTOR will complete the Service Order with relevant information. CONTRACTOR shall provide supporting documents as required therein and promptly return to CLIENT for review.

- CLIENT shall review the Service Order together with other information provided by CONTRACTOR and shall provide its comments / approval in due course.

- CONTRACTOR shall only proceed with the respective SERVICES after CLIENT provides the duly approved Service Order to CONTRACTOR, and in accordance with the mobilization instructions provided by CLIENT.

No compensation shall be made for any SERVICES performed by CONTRACTOR without a Call-Off Work Order as prior approved by CLIENT.

  - Completion of the SERVICES

Completion of the SERVICES under each Service Order will be formally documented depending upon the nature of the SERVICES as detailed hereunder.

For procurement related SERVICES, whereas CLIENT will provide the estimated duration of the SERVICES in the respective Call Off Work Order, CONTRACTOR shall notify CLIENT when the SERVICES were fully completed within the formal Inspection Reports as will be accompanied by a detailed timesheet for approval by CLIENT.

For other SERVICES, CLIENT shall notify CONTRACTOR when the SERVICES will be completed and the date of mobilization for PERSONNEL.

Regardless of the above procedures, CONTRACTOR is responsible for ensuring that the commencement and completion of SERVICES is fully documented as is required for invoicing purposes.

  - CHANGES

Whenever:

    - CLIENT issues a notice of CHANGE; or

    - CONTRACTOR considers that a CHANGE has occurred,

then CONTRACTOR shall submit a CHANGE ORDER Request Form as per Attachment 3 hereto.

A CHANGE ORDER Request Form, reference Attachment 3 hereto, shall be submitted to CLIENT by CONTRACTOR within five (5) DAYS and shall contain:

    - A detailed description of the CHANGE including CONTRACTOR’s reasoning and contractual references behind its opinion for the subject matter to be a CHANGE, reference to how / identification of whom initiated the alleged CHANGE and the latest date by which approval is sought in order not to impact the CONTRACT SCHEDULE;

    - A schedule for the execution of the alleged CHANGE indicating an estimate of the required resources and impact upon Milestones;

    - An estimate of the impact (if any) on the CONTRACT PRICE complete with full details of the cost build up to the lowest available level of data; and

    - An estimate and justification of CONTRACTOR’s estimate of the effect (if any) on the CONTRACT SCHEDULE (which shall be cumulative to address all previous and prevailing CHANGES to the SERVICES).

CLIENT will review the CHANGE ORDER Request Form and will respond accordingly.  When requested, CONTRACTOR shall issue a revised CHANGE ORDER Request Form as per CLIENT requirements and/ or the respective CHANGE ORDER within three (3) DAYS.  The revised CHANGE ORDER Request Form and / or the respective CHANGE ORDER, reference Attachment 3 hereto, shall contain the revised or as agreed details as addressed above.

  - CHANGE of the SERVICES

All of CONTRACTOR's obligations under the CONTRACT shall apply to any CHANGE unless otherwise specified in the respective CHANGE documentation.

The effect of a CHANGE on the CONTRACT PRICE shall be calculated by CONTRACTOR in accordance with Section 6.2 above and EXHIBIT II- COMPENSATION. To the maximum extent possible, CONTRACTOR is obligated to eliminate, reduce or mitigate the effect of any CHANGE on the CONTRACT PRICE.

The effect of a CHANGE on the CONTRACT SCHEDULE shall be agreed between CLIENT and CONTRACTOR on the basis of the net effect of such CHANGE with reasonable consideration being given to the accumulated effects of all previous CHANGES. To the maximum extent possible, CONTRACTOR shall take reasonable steps to eliminate, reduce or mitigate the effects of any CHANGE on the CONTRACT SCHEDULE.

  - CHANGE Register

CONTRACTOR shall maintain a CHANGE Register containing as a minimum the following:

- 	CONTRACTOR’s CHANGE Request number/identifier;

-	CHANGE Request issue date;

-	CLIENT’s number/ identifier;

-	The effect on the CONTRACT PRICE, as proposed by CONTRACTOR;

-	CHANGE Request status – “Pending/Disputed/Approved/Withdrawn”;

-	Approved CHANGE number/ identifier;

-	Approved CHANGE summary descriptive text;

-	CHANGE ORDER approval date;

-	The agreed adjustment on the CONTRACT PRICE, as approved by CLIENT;

-	The agreed adjustment on the CONTRACT SCHEDULE and/or Key Milestone Dates, as approved by CLIENT; and

-	Reference to other relevant documentation

CONTRACTOR shall keep the CHANGE register current and shall issue a copy to CLIENT with the monthly progress report in accordance with Section 5.3.2 above or as otherwise requested by CLIENT.

  - Issue and approval of CHANGE

Each CHANGE required in accordance with the provisions of the CONTRACT shall be authorized by means of CLIENT’s authorized representative signing the relevant CHANGE ORDER.

Unless expressly requested or instructed to do so by CLIENT, CONTRACTOR is not authorized to put a CHANGE into effect until it has received the relevant CHANGE ORDER duly approved by CLIENT’s authorized representative.

# Cost Management, Invoicing and Payment

  - General Procedures

Not later than thirty (30) DAYS after the EFFECTIVE DATE, CONTRACTOR shall submit for approval, its proposed procedures for accounting, financial control, forecasting, and invoicing under the CONTRACT. Such procedures shall ensure that CONTRACTOR maintains proper internal checks and financial control of all transactions under the CONTRACT and that the invoicing thereof is reliable, accurate and auditable. The procedures shall interface and be integrated with other procedures such as cost control, cost forecasting and planning. The procedures shall allow for review by the CLIENT REPRESENTATIVE or his nominated delegate of the proforma monthly invoice proposed by CONTRACTOR, as per EXHIBIT II, prior to its formal issue.

In particular, CONTRACTOR procedures shall address reporting of the full tracking of PERSONNEL deployed to the SERVICES, including location, names, job title, start date, current status, end dates, unit rates, both on an as incurred and forecast basis. The objective is to provide full visibility of resources and charges incurred under the CONTRACT, and as forecast for the foreseeable future based on known assignments.

  - Timesheets

PERSONNEL shall complete timesheets on a Daily Basis with brief details of the SERVICES performed during each day. For longer term assignments, all timesheets shall be presented for signing by CLIENT in a timely manner and at least on a weekly basis. PERSONNEL working on short term assignments (e.g. procurement related) shall present their timesheets for approval by CLIENT immediately upon completion of the associated SERVICES, along with a copy of the report produced in response to the subject SERVICES.

  - Invoicing

CONTRACTOR shall issue invoices in accordance with the requirements stipulated in EXHIBIT II. CONTRACTOR shall submit one (1) original and one (1) copy of each invoice to the address stated in EXHIBIT II, Section 3.3.

CONTRACTOR shall strictly follow the requirements related to invoicing as stipulated in GENERAL TERMS AND CONDITIONS and EXHIBIT II- COMPENSATION.

  - Supporting Documentation

CONTRACTOR shall support each invoice with appropriate documentation as necessary to substantiate the costs being invoiced are approved and have been accepted or approved by CLIENT. Such documentation shall comply with the specific requirements stipulated in EXHIBIT II, Section 3.

  - Close Out of Call-Off Work Orders

Upon completion of each Call-Off Work Order, CONTRACTOR shall represent the Call-Off Work Order to CLIENT for further signing by signing Section 8 therein to confirm that the SERVICES addressed have been fully completed and paid for by CLIENT.

  - Financial Close Out

Upon completion of all of the SERVICES, CONTRACTOR shall sign a Financial Close Out Certificate as issued by CLIENT to confirm the final CONTRACT PRICE and that CONTRACTOR has been paid in full by CLIENT. The COMPLETION CERTIFICATE shall be attached to the Financial Close Out Certificate.

# Representatives of the PARTIES

Representatives of the PARTIES are addressed in GENERAL TERMS AND CONDITIONS, Article 4.

# CONTRACT Close Out

Within one (01) month of the SERVICES having been completed, as addressed under Exhibit 1, Clause 7 therein, CONTRACTOR shall submit a formal “CONTRACT Close Out Report” addressing as a minimum:

- General Summary of CONTRACT with overview of CONTRACTOR’s performance of the SERVICES

- Overview of CONTRACTOR Organization, resources deployed and manhours expended (planned and actual by discipline).

- List of Deliverables under the CONTRACT.

- CONTRACT Price Summary (original and final).

- CHANGE Register with details of the CHANGES and the costs involved.

- Lessons Learned/ Opportunities for Improvement.

- Best Practices.

- Pending Matters and Handover.

- Contact(s) for further information.

The CONTRACT Close Out Report (if required) as accepted by CLIENT shall be required prior to the invoice for the final one complete month of the SERVICES being submitted to CLIENT.

# Attachments

Attachment 1 -	CONTRACTOR’s Organization Chart

Attachment 2 -	KEY PERSONNEL

Attachment 3 -	CHANGE ORDER PROPOSAL

Attachment 4 -	Call-Off Work Order Form

Attachment 5 -	Cost, Time and Resource (CTR) Form

ATTACHMENT 1

CONTRACTOR’S ORGANIZATION CHART

[ TAKEN FROM THE SUCCESSFUL BID ]

ATTACHMENT 2

KEY PERSONNEL

[ TAKEN FROM THE SUCCESSFUL BID ]

ATTACHMENT 3

CHANGE ORDER PROPOSAL

Changes to the WORKS, may be required during the performance of WORKS any extension of the CONTRACT and should be handled expeditiously and effectively by the Parties hereto.  Such changes may include but not be limited to additions, deletions, substitutions, alterations and modifications.

CLIENT shall have the right, at any time, to make any change but such change shall in no way affect the rights or obligations of the Parties hereto except as provided in a written Change Order.  Changes shall be carried out in accordance with the provisions of the CONTRACTOR.

Except as provided below, CONTRACTOR shall not proceed with any change prior to receipt of a Change Order, unless authorized in writing by the CLIENT’s Representative.

The procedure for handling and issuing Change Order(s) shall be as follows:

1.0	CHANGE ORDER REQUEST

1.1 	Whenever CLIENT requires an addition or deletion to Services from CONTRACTOR it shall issue to CONTRACTOR a Change Order Request inviting CONTRACTOR to submit a proposal based on a specific Scope of Work.

1.2  	CONTRACTOR shall submit its proposal to CLIENT in accordance with Section 2.0 hereof.

2.0	CHANGE ORDER PROPOSAL

2.1   Unless specified to the contrary, CONTRACTOR’s Change Order Proposal will be submitted to CLIENT within three (3) days to include a summarized Technical and Commercial Proposal as per APPENDIX 1.

2.2  	The Technical Proposal will divide the scope into relevant CTRs (Cost, Time and Resource Sheets). Each sheet describing a particular activity to be performed with a list of dependencies for input and output and a list of deliverables, and when requested by the Change Order Request will include:

(a)   Manpower Histogram

This shall support the CONTRACTOR’s proposed program to demonstrate that the CONTRACTOR can provide the planned resources for the specific Service Order.

(b)  Manpower Tabulation

A tabular breakdown of the histogram by major discipline and subdivided by lead engineer, senior engineer, engineer, drafting and other personnel categories.

(c)  Organization Chart

This shall identify proposed position and reporting relationships specific to the Service Order and shall include details of project team with resumes of all personnel for CLIENT approval.

(d) Barchart Schedule

This shall show the timing of all CTRs and all hold points for drawings such as HAZOP reviews, and a preliminary deliverable schedule.

2.3 The Commercial Proposal shall be priced out in accordance with EXHIBIT II -  COMPENSATION.  It will include as a minimum:

(a) Listing all CTRs;

(b) Priced CTR summary; and

(c) Summary cost per personnel category including total manhours and costs.

2.4 CLIENT will review CONTRACTOR’s Change Order Proposal and advise CONTRACTOR of the required actions.  CONTRACTOR shall not proceed with any additional Services until approval in writing is given by CLIENT authorizing CONTRACTOR to commence the additional Services.

3.0	CHANGE ORDER

3.1  When CLIENT approves CONTRACTOR’s Change Order Proposal, CLIENT will issue to CONTRACTOR a completed and signed CHANGE ORDER form for execution of the additional Services in the form appearing in the Form below.

3.2  In cases of extreme urgency for which CONTRACTOR is unable to submit a firm proposal prior to commencement of work on the necessary change, CLIENT may issue a "Preliminary Change Order" to authorize CONTRACTOR to proceed with the change on the basis of an approximate written estimate prepared by CONTRACTOR. As soon as possible thereafter, CONTRACTOR shall submit a Change Proposal giving its firm price for the change.  If the firm price quoted in the Change Proposal is more than that quoted in the "Preliminary Change Order", CONTRACTOR shall furnish CLIENT with the reasons for the differences.  Upon agreement of the Parties on the firm price, a Change Order shall be issued.

3.3   All communication on any Service Order authorization shall bear the CHANGE ORDER reference number assigned to them.

ATTACHMENT 4

CALL-OFF WORK ORDER

| - Contract Reference |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project |  | : Dai Hung Nam Project, Dai Hung Field Development, Block 05-1(a) |  |  |  |  |
| Contract No |  | : |  |  |  |  |
| Contract Title |  | : Marine Warranty Survey Services |  |  |  |  |
| - Call-Of Work Order No.: |  |  | Rev. No.: |  | Date: |
| To | : |  |  | From | : PVEP POC |
| Attn | : |  |  | Represented by | : …………………………………. (CLIENT Representative) |
| Tel | : |  |  | Tel | : |
| Fax | : |  |  | Fax | : |
| Email | : |  |  | Email |  |

- Description of Scope of Work:

| - Work Schedule: |  |
| --- | --- |
| Job Title | : …………………………………………… |
| Class Level | : …………………………………………… |
| Unit Rate Payable | : …………………………………………… |
| Mobilization Location | : …………………………………………… (procurement related only) |
| Work Location | : …………………………………………… |
| Work Duration | : ……………. DAYS / months tentatively including travelling time |
| Start Date | : ………/ …………. / 20….. (tentative) |
| Finish Date | : ………/ …………. / 20…..(tentative) |

| 5. Basis of Cost: |  |  |  |
| --- | --- | --- | --- |
| Unit Rate Reimbursable Lump Sum | Estimated Work Order Value: - __________ USD (as per Attachment 1) | Estimated Airfare Cost: (b) __________ USD Estimated Accomodation Cost: (c ) __________ USD (as per Attachment 3) | Estimated Other Costs: (d) __________ USD (to be substantiated) |
| Total Estimated Cost (a+b+c+d): _________________ USD/VND Remarks: Payment shall be made in accordance with the CONTRACT. |  |  |  |

6. Attachments:

- CTR (as per Attachment 5 of Exhibit III) - CV of personnel nominated by CONTRACTOR to perform the work - CONTRACTOR is to attach prices from airlines and hotels - …etc.

| 7. Approvals: |  |  |
| --- | --- | --- |
| Prepared by: Signature: ___________________ Name: ___________________ Date: ___________________ | Reviewed by: Signature: __________________ Name: __________________ Date: __________________ | Approved by CLIENT Rep.: Signature: _________________ Name: __________________ Date: __________________ |

| 8. Close Out of Call-Off Order: CONTRACTOR hereby confirms that the SERVICES provided under this Call-Off Work Order have been completed by CONTRACTOR and the respective invoices for all of the related SERVICES have been paid by CLIENT. Commencement Date of SERVICES: ______________________________ Completion Date of SERVICES: ______________________________ Date of Final Payment by CLIENT: ______________________________ |  |
| --- | --- |
| Presented by CONTRACTOR: Signature: ____________________________ Name: ____________________________ Date: ____________________________ | Approved by CLIENT REPRESENTATIVE: Signature: ______________________________ Name: _______________________________ Date: _______________________________ |

ATTACHMENT 5

COST, TIME AND RESOURCE (CTR) FORM

| COST TIME RESOURCE (CTR) FORM |  |  |  |  | CTR No.: |  |
| --- | --- | --- | --- | --- | --- | --- |
| CONTRACT: |  |  |  |  | Revision: |  |
| Originator: |  |  |  |  | Date: |  |
| Approved By (Contractor): |  |  |  |  | Task No.: |  |
| (Incumbent Name / Date) |  |  |  |  |  |  |
| Planned Start Date: |  |  | Planned Completion Date: |  |  |  |
| Call-Off Work Order No. Reference: |  |  |  |  |  |  |
| Activity Scope: |  |  |  |  |  |  |
| Assumptions: |  |  |  |  |  |  |
| Attendances: |  |  |  |  |  |  |
| Input for Activity: |  |  |  |  |  |  |
| Deliverables from Activity: |  |  |  |  |  |  |
| Resources: |  |  | Planned Duration (Days/Months) | Daily/ Monthly Rate (USD) |  | Costs USD |
| 1 |  |  |  |  |  | $ - |
| 2 |  |  |  |  |  | $ - |
| 3 |  |  |  |  |  | $ - |
| 4 |  |  |  |  |  | $ - |
| 5 |  |  |  |  |  | $ - |
| 6 |  |  |  |  |  | $ - |
| 7 |  |  |  |  |  | $ - |
| 8 |  |  |  |  |  | $ - |
| Subtotal: |  |  | 0 | Subtotal: |  | $ - |
| Trip | From City / Country | To City / Country | Airfare USD/VND | Number of Travel Days | Travel Per Diem USD | Cost USD/VND |
| 1 |  |  |  |  |  | $ - |
| 2 |  |  |  |  |  | $ - |
| 3 |  |  |  |  |  | $ - |
| 4 |  |  |  |  |  | $ - |
| 5 |  |  |  |  |  | $ - |
| Subtotal: |  |  |  | 0 | Subtotal: | $ - |
| Total CTR Cost (USD) |  |  |  |  |  | $ - |